## DEVELOPMENT LOG
DEVELOPMENT LOG
PROJECT NAME | Event Recommender System
PROJECT ID
PROJECT MANAGER | Jayanth G S
DOCUMENT VERSION | 1 AND 2
PROJECT START DATE | 2020-06-15
PROJECT END DATE | 2020-07-31
SL NO | FEATURE NAME | VERSION 1 LINK | VERSION 1 CREATION DATE | VERSION 2 LINK | VERSION 2 CREATION DATE | VERSION CHANGE DESCRIPTION | DEVELOPMENT STATUS | REVIEW STATUS | COMMENTS
1 | Dataset Collected | VERSION 1 | 2020-07-06 | VERSION 2 | 2020-07-16 | New column added for event type and additional datacollected based on it | COMPLETED | REVIEWED
2 | Data Preprocessing/Feature Engineering and Training and Testing Data Split | VERSION 1 | 2020-07-10 | VERSION 2 | 2020-07-20 | Data encoding is changed and two separate classes for feature engineering . | COMPLETED | REVIEWED
3 | Generating features with TFIDF Vectors and Unigrams using Chi squared test | VERSION 1 | 2020-07-10 | VERSION 2 | 2020-07-20 | Feature engineering computation is performed based on two target classes i.e Domain and event type | COMPLETED | REVIEWED
4 | Training classifiers with Algorithms -Using Random Search and Grid Search Cv for fine tunning the parameters for domain type -Selecting Grid Search CV hyperparameters to train the model. | VERSION 1 | 2020-07-13 | VERSION 2 | 2020-07-23 | Considering a second classifier to train on Event Type pivot using Random Forest Algorithm | COMPLETED | REVIEWED
5 | Experimenting text inputs and generating results. -In version 1 we are only classifying based on domain | VERSION 1 | 2020-07-15 | VERSION 2 | 2020-07-25 | In version 2 we are classifying based on domain as well as event type | COMPLETED | REVIEWED