## Sheet1
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | Event Recommender System
PROJECT SPONSOR | Cloud Counselage Pvt Ltd
PROJECT MANAGER | Jayanth G S
EXPECTED START DATE | 2020-06-15
EXPECTED COMPLETION DATE | 2020-07-31
ESTIMATED COST
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE | • To read a set of events as input. • To classify each event into one or more domains. • To fetch the employee database with domain and event preferences. • To match each event with all interested employees. • To output the list of matching employees per event.
BUSINESS CASE | One often misses events of interest sheerly due to a lack of awareness at the right time. Cloud Counselage also receives invites for events in multiple domains that need to be forwarded to people with relevant interests. The aim is to create a Recommender System that recommends only relevant events to each employee and intern based on their preferences, whenever the company receives invites for said events. The system should read new events and autonomously classify them into various domains. It should then match the event with all of those in the company database who have given said domains as a preference. Finally, for each event, the system should output the list of people whose preferences match with the event’s detected domain.
GOALS/METRICS | To create a Event Recommendor system to various interns based on their interest domain
EXPECTED DELIVERABLES | An Event Recommendor System with features that are going to benefit both the interns, employee's and learners
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE | Classify the events in various domains using machine learning techniques and taking the inputs from user generated an excel sheet of employee/intern name who can be interested in the event.
OUTSIDE OF SCOPE | To have a User Interface for the project. The project will mainly involve the machine learning technology
PROJECT RESOURCES AND COSTS
PROJECT TEAM | Kiara, Zenith, Siddharth
SUPPORT RESOURCES | Laptops with 64 bit and minimum 8GB RAM, Jupyter Notebook Environment and Electricity
SPECIAL NEEDS
PROJECT BENEFITS AND CUSTOMERS
PROCESS OWNER | Trishala Ahalpara
KEY STAKEHOLDERS | Jayanth G S, Nirbhey Singh Pahwa
END CUSTOMER | Cloud Counselage
EXPECTED BENEFIT
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS | Techical risk: Unmet requirements-forgetting to include a single requirement can cost us time & budget overhead, or worse, poor website quality. Resource risk: Uncertainty in resource availability: Interns might go on leave on commencement of university exams. Due to the COVID-19 outbreak, the exact examination dates are not available. On team change over, new members needs to get trained and it's time-consuming. Also, the current team members lack knowledge in back-end development. This might result in the escalation of project completion.
ASSUMPTIONS | Event Recommendor system will help the event organizers to find out the employees/intern who are interested in a particular domain.
CONSTRAINTS | Only a month and a half is given to complete the project can lead to the quality deteoriation for the software development. Some design constraints are: • The system is to be created in Python 3.6 or above. • The events and employee list to be read shall be provided as a [txt] with 1 element per line. • You are allowed to use any ML approach, publicly available resources, and additional training data, but the final output should be on the provided list. • The output shall be in the form of a spreadsheet having a column for event name and another for the names of people to recommend said event to. • The output spreadsheet should be auto-generated by the system you create.