## Sheet1
PROJECT PLAN FOR EXECUTION PHASE
PROJECT NAME | Event Recommendation System
PROJECT MANAGER | JAYANTH G S |  | EXECUTION PHASE START DATE:
PROJECT DELIVERABLE |  |  | EXECUTION PHASE END DATE:
PROJECT SCOPE
PROJECT START DATE | 2020-06-15
PROJECT END DATE | 2020-07-31
OVERALL PROGRESS | In Progress
PARENT FEATURE | FEATURES | REQUIRED TIME (IN HRS) | START DATE | END DATE | DURATION IN DAYS | STATUS
1. Initiation | 1.1 Identify business problem |  | 2020-06-15 | 2020-06-21 | 7 | COMPLETED
| 1.2 Recruit a team |  | 2020-06-15 | 2020-06-21 | 7 | COMPLETED
| 1.3 Create a project charter |  | 2020-06-22 | 2020-06-28 | 7 | COMPLETED
| 1.4 Requirement gathering |  | 2020-06-22 | 2020-06-28 | 7 | COMPLETED
2 Planning | 2.1 Approval of business process |  | 2020-06-29 | 2020-07-05 | 7 | COMPLETED
| 2.2 Baseline project plan |  | 2020-06-29 | 2020-07-05 | 7 | COMPLETED
| 2.3 Team roles and responsibilities |  | 2020-06-29 | 2020-07-05 | 7 | COMPLETED
3 Execution | 3.1 Finalize design |  | 2020-07-06 | 2020-07-15 | 10 | COMPLETED
| 3.2 Build |  | 2020-07-16 | 2020-07-31 | 16 | COMPLETED
3.2.1 Features
| 1)Data Collection -Generating dataset manually from emails/coursera (123 data set, equally sampled in their respectice domain) |  | Version 1 : 06-07-2020 Version 2: 16-07-2020 | Version 1: 09-07-2020 Version 2: 19-07-2020 | 8 | COMPLETED
| 2) Data Preprocessing/Feature Engineering -Data Cleaning -Removing quotes -Lowering the text case -Removing punctuations -Eliminating Possessive pronouns -Word Lemmatization -Removing stop words |  | Version 1: 10-07-2020 Version 2: 20-07-2020 | Version 1: 12-07-2020 Version 2: 22-07-2020 | 6 | COMPLETED
| 3) Training test data Split -Taking 70 percent of data has training and 30 percent as test. |  | Version 1: 10-07-2020 Version 2: 20-07-2020 | Version 1: 12-07-2020 Version 2: 22-07-2020 | 6 | COMPLETED
| 4) Generating features with TFIDF Vectors and Unigrams using Chi squared test |  | Version 1: 10-07-2020 Version 2: 20-07-2020 | Version 1: 12-07-2020 Version 2: 22-07-2020 | 6 | COMPLETED
| 5) Training the labelled data set and generated features with Random Forest Classifier -Using Random Search and Grid Search Cv for fine tunning the parameters. -Selecting Grid Search CV hyperparameters to train the model. |  | Version 1: 13-07-2020 Version 2: 23-07-2020 | Version 1: 14-07-2020 Version 2: 24-07-2020 | 4 | COMPLETED
| 3.3 Testing of Domain Classification 1)Generating Training and Test set accuracy 2)Generating Classification report 3) Manual Testing -Class code encoding -Take random text of event/course -Perform data cleaning and feature engineering on the input text -Using trained classifier predicting the domain of the input text |  | Version 1: 15-07-2020 Version 2: 25-07-2020 | Version 1: 16-07-2020 Version 2: 26-07-2020 | 4 | COMPLETED
| 3.4 Generating employee details based on domain andevent type -Fetching predefined employee details excel sheet -Based on the predicted domain and event type, generating the list of employees interested in the event |  | Version 1: 15-07-2020 Version 2: 25-07-2020 | Version 1: 16-07-2020 Version 2: 26-07-2020 | 4 | COMPLETED
4. Closure |  |  | 2020-07-31 | 2020-07-31 | 1 | COMPLETED