## RAID LOG
| RAID Log | [9 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 2 | 0 | 1 | 0 | 0 | 0
| Project title: | Event Recommender System |  | Project Id: |  | Project Manager: | Jayanth G S |  |  | Assumption | 1 | 0 | 0 | 1 | 0 | 0
[10 empty] | Issue | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Last Updated date: | 2020-07-26 | Project Team Lead: | Aarya Bodhankar |  |  | Dependency | 1 | 0 | 0 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 4 |  |  |  |  | 2
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | RISK | Inability to find legit data for the model | The accuracy and results generated may not be trusted for professional use | Have a data vendor available who can provide the dataset | Project Manager | High |  | Open | Risk
2 | RISK | Machine Learning Model to be selected | Sometimes some kind of data doesn't gives legit results with poorly trained machine learning models. The algorithm selected and used plays an important role | Have a machine learning engineer /data scientist who can guide the developers by suggesting which kind of model will work best with out dataset | Project Manager | Moderate |  | Closed | Assumption
3 | Assumption | We are assuming a limited amount of classes as in domains and event type. For domain we are considering 8 categories and for event type we are considering 5 categories | This may impact on the classification of categories we are not considering. | As such the only solution is to collect a sampled dataset involving all the categories of domain and event type | Project Manager | Moderate |  | Open | Issue
4 | Dependency | The ml model for our projected is highly depended on the dataset collected | If the dataset collected for training is not legit this may impact on the accuracy of their results | Valid sources or vendors to be used for collection of data | Project Manager | Moderate |  | Closed | Dependency
5
6 | [8 empty] | Open
7 | [8 empty] | Closed
8
9 | [8 empty] | Critical
10 | [8 empty] | High
11 | [8 empty] | Moderate
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24